HERBAL REMEDIES SURVEY PROJECT

PROJECT PLAN

Project Title:

Herbal Remedies Survey Project

Project Type:

Survey Data Collection, Data Analysis and Visualization

Project Status:

Completed

Final Analytical Dataset:

60 Respondents

Primary Tools:

KoboToolbox

CommCare

Google Forms

Microsoft Excel

Microsoft SQL Server

Microsoft Power BI

1. PROJECT PLAN PURPOSE

This project plan documents the planned workflow, activities, analytical stages, deliverables, tools, quality assurance activities, and completion criteria for the Herbal Remedies Survey Project.

The plan was designed to provide a structured approach for moving the project from survey data collection through data preparation, analysis, visualization, documentation, and final reporting.

2. PROJECT GOAL

The overall goal of the project was to develop a complete and professionally documented survey analytics project examining the use of herbal remedies among the surveyed respondents.

The project combines digital data collection, data preparation, structured analysis, visualization, quality assurance, and reporting.

3. PROJECT OBJECTIVES

The project was planned to achieve the following objectives:

1. Collect survey responses through digital data collection platforms.

2. Consolidate the collected survey data.

3. Prepare and clean the analytical dataset.

4. Analyze demographic characteristics of respondents.

5. Analyze herbal remedy usage patterns.

6. Identify commonly reported herbal remedies.

7. Examine usage frequency.

8. Assess perceived effectiveness.

9. Examine recommendation behavior.

10. Analyze reported side effects.

11. Develop an Excel analytical dashboard.

12. Perform structured SQL analysis.

13. Develop an interactive Power BI dashboard.

14. Validate analytical results across tools.

15. Produce professional technical documentation.

16. Produce a final presentation.

4. PROJECT SCOPE

The project scope covered the complete analytical lifecycle from survey data collection to final reporting.

The scope included:

- Digital survey data collection

- Data consolidation

- Data preparation

- Data cleaning

- Exploratory data analysis

- Descriptive analysis

- SQL analysis

- Excel analysis

- Dashboard development

- Power BI visualization

- Quality assurance

- Cross-tool validation

- Documentation

- Final presentation

5. PROJECT PHASES

The project was organized into the following major phases:

PHASE 1 — DATA COLLECTION

PHASE 2 — DATA CONSOLIDATION

PHASE 3 — DATA PREPARATION AND CLEANING

PHASE 4 — EXCEL ANALYSIS

PHASE 5 — SQL ANALYSIS

PHASE 6 — POWER BI DEVELOPMENT

PHASE 7 — QUALITY ASSURANCE

PHASE 8 — DOCUMENTATION

PHASE 9 — FINAL PRESENTATION

PHASE 10 — PROJECT CLOSURE

6. PHASE 1 — DATA COLLECTION

Purpose:

To obtain survey responses through the selected digital data collection platforms.

Platforms:

KoboToolbox

CommCare

Google Forms

Activities:

- Configure survey instruments.

- Collect respondent submissions.

- Monitor collected records.

- Review incoming responses.

- Preserve the source datasets for consolidation.

7. PHASE 2 — DATA CONSOLIDATION

Purpose:

To bring survey records from the different collection platforms into a common analytical structure.

Activities:

- Export source datasets.

- Review field structures.

- Align corresponding variables.

- Standardize field names.

- Combine the records.

- Identify the original collection source.

- Prepare the consolidated analytical dataset.

8. PHASE 3 — DATA PREPARATION AND CLEANING

Purpose:

To ensure that the consolidated dataset was suitable for analysis.

Activities:

- Review column structure.

- Standardize categorical values.

- Review missing values.

- Review inconsistent responses.

- Check respondent records.

- Confirm analytical fields.

- Prepare the final dataset.

Output:

Final analytical dataset containing 60 respondent records.

9. PHASE 4 — EXCEL ANALYSIS

Purpose:

To perform exploratory and descriptive analysis using Microsoft Excel.

Activities:

- Review cleaned data.

- Calculate key indicators.

- Create pivot tables.

- Analyze respondent demographics.

- Analyze herbal remedy usage.

- Analyze usage frequency.

- Analyze perceived effectiveness.

- Analyze recommendation behavior.

- Analyze reported side effects.

- Rank herbal remedies.

- Create analytical charts.

- Develop Excel dashboard.

10. EXCEL DASHBOARD DELIVERABLE

The Excel dashboard was designed to provide a concise visual summary of the survey findings.

The final dashboard uses six analytical charts:

1. Gender Distribution

2. Respondents by Age Group

3. Top 5 Most Used Herbs

4. Herbal Remedy Usage Frequency

5. Perceived Effectiveness

6. Reported Side Effects

11. PHASE 5 — SQL ANALYSIS

Purpose:

To provide a structured relational analysis and validation layer.

Activities:

- Import the prepared dataset.

- Validate the analytical table.

- Review available fields.

- Validate record count.

- Review categorical values.

- Perform grouped analysis.

- Calculate analytical indicators.

- Rank herbal remedies.

- Validate Excel results.

- Produce SQL documentation.

12. SQL ANALYTICAL OUTPUTS

The SQL stage supported analysis of:

- Total respondents

- Herbal usage

- Perceived effectiveness

- Recommendation rate

- Reported side effects

- Demographic distributions

- Usage frequency

- Reasons for use

- Sources of herbal remedies

- Herbal remedy rankings

- Data-source distributions

13. PHASE 6 — POWER BI DEVELOPMENT

Purpose:

To transform the validated analytical dataset into an interactive business intelligence dashboard.

Activities:

- Import analytical data.

- Review Power Query preparation.

- Configure the data model.

- Create analytical measures.

- Create KPI cards.

- Create six analytical charts.

- Create interactive slicers.

- Apply the project theme.

- Configure visual interactions.

- Validate dashboard calculations.

- Perform final dashboard QA.

14. POWER BI DASHBOARD DELIVERABLE

The final Power BI dashboard contains:

5 KPI Cards

6 Analytical Charts

3 Interactive Slicers

1 Professional Dashboard Theme

1 Executive Dashboard Page

15. POWER BI KPI STRUCTURE

The five KPI indicators are:

1. Total Respondents

2. Herbal Usage

3. Perceived Effectiveness

4. Recommendation Rate

5. Reported Side Effects

16. POWER BI FILTER STRUCTURE

The three interactive slicers are:

1. Gender

2. Location

3. Age Group

These filters allow users to explore the dashboard according to selected respondent characteristics.

17. PROJECT DESIGN STANDARD

The project follows a consistent visual design standard.

Primary dashboard accent:

#2E7D32

Primary font:

Segoe UI

The design principles include:

- Consistent typography

- Consistent colors

- Clear visual hierarchy

- Appropriate spacing

- Clean dashboard layout

- Minimal visual clutter

- Professional analytical presentation

18. PHASE 7 — QUALITY ASSURANCE

Quality assurance was performed throughout the project lifecycle.

The QA process included:

- Data structure validation

- Record count validation

- Category validation

- KPI validation

- Pivot-table validation

- Chart validation

- SQL validation

- Power BI validation

- Slicer testing

- Cross-filter testing

- Dashboard layout review

- Final output review

19. CROSS-TOOL VALIDATION

Analytical results were compared across:

Microsoft Excel

Microsoft SQL Server

Microsoft Power BI

The validation focused on:

- Total respondent count

- Herbal usage rate

- Perceived effectiveness

- Recommendation rate

- Reported side effects

- Category distributions

- Herbal remedy rankings

20. VALIDATED PROJECT INDICATORS

The final validated indicators are:

Total Respondents:

60

Herbal Usage:

95.00%

Perceived Effectiveness:

91.67%

Recommendation Rate:

78.33%

Reported Side Effects:

36.67%

21. PHASE 8 — DOCUMENTATION

The documentation phase was planned to capture the methodology, analytical processes, technical outputs, and final project results.

Documentation deliverables include:

- Project Report

- Data Dictionary

- SQL Documentation

- Excel Documentation

- Power BI Documentation

22. PHASE 9 — FINAL PRESENTATION

The final presentation communicates the major project findings in a concise and visually structured format.

The presentation summarizes:

- Project background

- Survey objectives

- Data collection

- Respondent profile

- Herbal remedy usage

- Major analytical findings

- Perceived effectiveness

- Recommendation behavior

- Reported side effects

- Key conclusions

23. PHASE 10 — PROJECT CLOSURE

Project closure confirms that all planned analytical, visualization, documentation, and reporting deliverables have been completed.

Closure activities include:

- Final dashboard review

- Documentation review

- Folder structure review

- Deliverable verification

- Final quality assurance

- Portfolio-readiness review

- Project status update

24. KEY PROJECT DELIVERABLES

The completed project deliverables include:

1. Survey datasets.

2. Cleaned analytical dataset.

3. Excel analysis workbook.

4. Excel dashboard.

5. SQL analytical outputs.

6. Power BI dashboard.

7. Project report.

8. Data dictionary.

9. SQL documentation.

10. Excel documentation.

11. Power BI documentation.

12. Final presentation.

25. PROJECT TOOLS

Data Collection:

KoboToolbox

CommCare

Google Forms

Data Preparation and Analysis:

Microsoft Excel

Database Analysis:

Microsoft SQL Server

Business Intelligence:

Microsoft Power BI

Documentation and Reporting:

Microsoft Word

Microsoft PowerPoint

26. RESOURCE PLAN

The project required the following resources:

Data:

Survey responses from the selected collection platforms.

Software:

KoboToolbox

CommCare

Google Forms

Microsoft Excel

Microsoft SQL Server

Microsoft Power BI

Microsoft Word

Microsoft PowerPoint

Analytical Resources:

- Data cleaning procedures

- SQL queries

- Excel pivot tables

- Excel charts

- DAX measures

- Power BI visualizations

- Quality assurance procedures

27. QUALITY CONTROL CHECKPOINTS

Checkpoint 1:

Source data review

Status:

COMPLETED

Checkpoint 2:

Data consolidation

Status:

COMPLETED

Checkpoint 3:

Data cleaning

Status:

COMPLETED

Checkpoint 4:

Excel analysis validation

Status:

COMPLETED

Checkpoint 5:

SQL analysis validation

Status:

COMPLETED

Checkpoint 6:

Power BI validation

Status:

COMPLETED

Checkpoint 7:

Final documentation review

Status:

COMPLETED

Checkpoint 8:

Final project review

Status:

COMPLETED

28. PROJECT SUCCESS CRITERIA

The project successfully met its planned criteria when:

- The survey data was consolidated.

- The analytical dataset was finalized.

- 60 respondent records were available for analysis.

- Excel analysis was completed.

- SQL analysis was completed.

- Power BI dashboard was completed.

- Dashboard calculations were validated.

- Six final charts were implemented.

- Three interactive slicers were implemented.

- Documentation was completed.

- Final presentation was completed.

29. PROJECT STATUS

Overall Project Status:

COMPLETED

Data Collection:

COMPLETED

Data Preparation:

COMPLETED

Excel Analysis:

COMPLETED

SQL Analysis:

COMPLETED

Power BI Development:

COMPLETED

Quality Assurance:

COMPLETED

Documentation:

COMPLETED

Final Presentation:

COMPLETED

30. PROJECT COMPLETION SUMMARY

The Herbal Remedies Survey Project completed its planned data analytics lifecycle.

The project successfully moved from digital survey data collection through data consolidation, preparation, analysis, visualization, quality assurance, documentation, and final reporting.

The completed outputs provide a structured and reproducible demonstration of practical data analytics using Excel, SQL, and Power BI.

31. PROJECT PLAN APPROVAL

Project:

Herbal Remedies Survey Project

Plan Status:

COMPLETED

Final Status:

READY FOR PROJECT CLOSURE AND PORTFOLIO ARCHIVING