## Task_Tracker
HERBAL REMEDIES SURVEY PROJECT — TASK TRACKER
Task ID | Phase | Task Description | Tool / Platform | Deliverable | Dependency | Priority | Status | QA Status
T001 | Data Collection | Collect survey responses | KoboToolbox; CommCare; Google Forms | Raw survey datasets | None | High | COMPLETED | PASS
T002 | Data Consolidation | Export and consolidate source datasets | Microsoft Excel | Consolidated dataset | T001 | High | COMPLETED | PASS
T003 | Data Preparation | Review dataset structure and analytical fields | Microsoft Excel | Prepared dataset | T002 | High | COMPLETED | PASS
T004 | Data Cleaning | Standardize values and review data quality | Microsoft Excel | Clean analytical dataset | T003 | High | COMPLETED | PASS
T005 | Exploratory Analysis | Review respondent demographics and response distributions | Microsoft Excel | Exploratory analysis outputs | T004 | High | COMPLETED | PASS
T006 | Excel Analysis | Calculate KPIs and create pivot-table analysis | Microsoft Excel | Excel analytical workbook | T005 | High | COMPLETED | PASS
T007 | Excel Dashboard | Develop analytical charts and dashboard | Microsoft Excel | Excel dashboard | T006 | High | COMPLETED | PASS
T008 | SQL Setup | Import and prepare analytical dataset | Microsoft SQL Server | SQL analytical table | T004 | High | COMPLETED | PASS
T009 | SQL Analysis | Perform analytical queries and grouped analysis | Microsoft SQL Server | SQL analytical outputs | T008 | High | COMPLETED | PASS
T010 | SQL Validation | Validate SQL results against Excel analysis | Excel; SQL | Server | Validated analytical results | T009 | High | COMPLETED | PASS
T011 | Power BI Import | Import validated analytical dataset | Microsoft Power BI | Power BI dataset | T009 | High | COMPLETED | PASS
T012 | Power BI Model | Prepare Power BI analytical model | Microsoft Power BI | Data model | T011 | High | COMPLETED | PASS
T013 | DAX Measures | Create KPI measures | Microsoft Power BI | KPI measures | T012 | High | COMPLETED | PASS
T014 | Power BI Visuals | Create six final analytical charts | Microsoft Power BI | Six dashboard visuals | T013 | High | COMPLETED | PASS
T015 | Power BI Slicers | Create three interactive slicers | Microsoft Power BI | Three dashboard slicers | T014 | High | COMPLETED | PASS
T016 | Power BI Theme | Apply final dashboard theme and visual formatting | Microsoft Power BI | Professional dashboard theme | T014 | Medium | COMPLETED | PASS
T017 | Power BI QA | Test calculations, visuals, filters and interactions | Microsoft Power BI | Validated Power BI dashboard | T015; T016 | High | COMPLETED | PASS
T018 | Cross-Validation | Compare Excel, SQL and Power BI results | Excel; SQL; Power BI | Cross-validated results | T017 | High | COMPLETED | PASS
T019 | Documentation | Document project methodology and analytical workflow | Microsoft Word; Excel | Project documentation | T018 | High | COMPLETED | PASS
T020 | Final Presentation | Prepare final project presentation | Microsoft PowerPoint | Final presentation | T019 | High | COMPLETED | PASS
T021 | Project Review | Review all deliverables and folder structure | All project tools | Reviewed project package | T020 | High | COMPLETED | PASS
T022 | Project Closure | Close and prepare project for portfolio archiving | All project tools | Portfolio-ready project | T021 | High | COMPLETED | PASS

## Task_Summary
HERBAL REMEDIES SURVEY PROJECT — TASK SUMMARY
Metric | Value
Total Tasks | 22
Completed Tasks | 22
Outstanding Tasks | 0
Completion Rate | 100%
High Priority Tasks | 20
Medium Priority Tasks | 2
QA Passed | 22
QA Failed | 0
Project Status | COMPLETED

## Phase_Summary
HERBAL REMEDIES SURVEY PROJECT — PHASE SUMMARY
Phase | Tasks | Completed | Outstanding | Status
Data Collection | 1 | 1 | 0 | COMPLETED
Data Consolidation | 1 | 1 | 0 | COMPLETED
Data Preparation & Cleaning | 2 | 2 | 0 | COMPLETED
Exploratory Analysis | 1 | 1 | 0 | COMPLETED
Excel Analysis | 2 | 2 | 0 | COMPLETED
SQL Analysis | 3 | 3 | 0 | COMPLETED
Power BI Development | 7 | 7 | 0 | COMPLETED
Quality Assurance | 1 | 1 | 0 | COMPLETED
Cross-Validation | 1 | 1 | 0 | COMPLETED
Documentation | 1 | 1 | 0 | COMPLETED
Final Presentation | 1 | 1 | 0 | COMPLETED
Project Closure | 1 | 1 | 0 | COMPLETED